## Event Purpose & Objectives
EVENT NAME Date Time Location
Event Purpose & Overview:
Event Objectives:
WSU Mission: | To apply knowledge through local and global engagement that will improve quality of life and enhance the economy of the state, nation, and world.
WSU Strategic Goals: | Outreach & Engagement Goal 1: Increase access to and breadth of WSU’s research, scholarship, creative, academic, and extension programs throughout Washington and the world. Goal 2: Expand and enhance WSU’s engagement with institutions, communities, governments, and the private sector. Goal 3: Increase WSU faculty, staff, and students’ contributions to economic vitality, educational outcomes, and quality of life at the local, state, and international levels.
Contacts: | Name | email | Phone
Website: | if applicable

## Planning
PLANNING
Due Date | Status | Task/Action | Responsibility | Decisions/Comments
GENERAL
Meet with project coordinator, planning committee, and risk management personnel.
Determine planning meeting schedule, send Outlook invitations
Determine event purposes and objectives
Establish budget
Determine ticket price.
Establish areas of responsibility and roles
Make staff assignments for onsite hosting
Understand and be aware of cancellation clauses for all contracts
Secure appropriate permits (sound, parade, air, street, banquet, etc.)
Assess need for law enforcement, security, and/or safety personnel.
Plan for onsite crisis management and security.
Determine and communicate appropriate dress for staff.
Develop an executive briefing form of the event for briefing purposes
Assemble notebooks for day of event
Schedule a pre-event meeting with team 1-2 days prior to event
Send out Post-Event Evaluation to key stakeholders
A/V, LIGHTING, AND PHOTOGRAPHY
Determine photo needs; schedule photographer
Secure professional sound equipment and personnel
Research and determine lighting needs
Confirm wireless access
Schedule tech rehearsals
Perform sound and lighting checks
CATERING
Meet with caterer: select menu and wine, review timing of dinner service flow, assure adequate staffing
Taste test menu
Identify and plan for special diet concerns
Acquire appropriate alcohol/food permits, request to serve food forms
Guarantee final numbers to caterer
DECORATIONS
Determine decoration color scheme
Contract with vendors for decorations and technical support as needed
Order props or other décor
Order flowers and confirm pickup/delivery times
HOTELS
Secure hosts, logistical arrangements for out-of-town special guests and dignitaries
Confirm room block with hotels
Confirm hotel shuttle availability
Review hotel rooming lists and pickup reports
Identify VIPs for hotel amenity
PROGRAM
Determine desired content and length of written program
Confirm entertainment bookings; finalize contracts and arrangements with entertainers as needed
Outline various subject areas that need to be addressed from the podium as part of the program
Script speaking portions of the program
Determine dress rehearsal need(s)
Distribute script and program timeline to planning committee, production team, and program participants
SEATING AND REGISTRATION
Determine information that needs to be captured on RSVP page and back end
Plan overall registration/check-in process; ensure entrance to event is comfortable and process is welcoming
Enlarge a diagram of the room to be used as a seating chart
Determine seating plans, basic arrangements
Determine head table(s), proper placement of honored guest(s)
Finalize seating assignments and charts
Make nametags and placecards
Provide guest lists sorted by table number and by last name to staff on-site
Decide plan for unexpected walk-ins, nametag changes, last-minute questions, and handling money
SUPPLIES
Take delivery of all printed materials and favors
Gather event materials (including first aid kit)
TRANSPORTATION
Consult Parking and Transportation office regarding anticipated transportation needs
Arrange for shuttling service if needed
Arrange for adequate parking space and define staffing needs
VENUE
Determine and reserve venue (including alternate location for outdoor events in case of inclement weather or unforeseen circumstances)
Determine on-site contact
Determine venue restrictions (if any)
Produce layout drawings of event space
Address disability access and safety issues
Contact facilities to make sure event space will be cleaned and groomed
Secure adequate garbage cans
Arrange for coat check if needed
Order tables/chairs if needed

## Marketing
MARKETING
Due Date | Status | Task/Action | Responsibility | Decisions/Comments
GENERAL
Select a theme
Determine overall look and feel of all printed and web/html materials and communicate needs with Marketing Communications staff.
Determine deadline, copy deadline, costs, and partners
Determine which internal avenues will be used (WSU Today, WSU Announcements, Evergreen, Washington State Magazine, Social Media, Campus Digital Screens)
Determine which external avenues will be used (Community Update, Daily News, Chamber, Radio, Social Media)
Determine if venue has electronic display boards that are available for promotion.
INVITATIONS
Draft invitation copy, work with creative staff in Marketing Communications
Finalize invitation list
Send save the date card/email
Send invitation card/email
REGISTRATION
Website live
Record and acknowledge RSVPs as they are received; send maps, tickets, parking permits, and other specifics as needed to confirmed attendees.
If there is a fee associated with the event, manage receipts, cancellations, and refunds.
Send RSVPs to internal leadership and other constituents involved in program
COLLATERAL
Gather documentation and copy for written program
Determine written program distribution and placement
Print written program
Determine and make needed directional and welcome signage
Print table numbers
Get notebook cover from Marketing Communications

## Post Event Evaluation
Post Event Evaluation-Event Name
Statement/Goal |  | 1 | 3 | 5
|  | Strongly Disagree | Agree | Strongly Agree
I believe the [Event] has been a success.
Measurable Goals & Objectives
Copy from Event Purpose and Objectives
Did the [Event] fulfill the mission & goals set-forth by WSU as indentified with the 2014-2019 Strategic Plan:
Copy from Event Purpose and Objectives
I received adequate notice to fulfill my duties to the best of my capabilities.
Average % strongly agreed by group
Total number of respondents
Event Element |  | 1 | 3 | 5
|  | Unsatisfactory | Average | Excellent
Catering
Printed Materials: Invitation, Program, etc.
Décor
Speakers
Set-Up
A.V.
Overall flow of event
Entertainment
Registration
Venue
Parking & Directions
Average % ranked excellent by group
Total number of respondents

## Budget
Event Name
Date
Expenses - Working Budget
ITEMS |  |  | NOTES
VENUE/LECTURE | ESTIMATE | ACTUAL
SUBTOTAL
RECEPTION | ESTIMATE | ACTUAL
SUBTOTAL
DECORATIONS | ESTIMATE | ACTUAL
SUBTOTAL
MARKETING EXPENSES | ESTIMATE | ACTUAL
SUBTOTAL
DIGITAL AND PRINTED MATERIALS | ESTIMATE | ACTUAL
SUBTOTAL
MISC. EXPENSES | ESTIMATE | ACTUAL
SUBTOTAL
TOTAL EXPENSES

## Day Of Tasklist
| To-Do | Location | Responsibility
Date
Date